## Risk Register
ID | Category | Risk description | Asset / service | Likelihood 1-5 | Impact 1-5 | Inherent score | Risk band | Residual (est.) | Treatment | Owner | Target | Status
R-01 | Access | Administrative account at a critical third-party service without multi-factor authentication | Third-party service | 3 | 5 | 15 | High (15-25) | 5 | Enable MFA (hardware key or TOTP). | Security Lead | Week 1 | Open
R-02 | Access | Privileged productivity-suite account without MFA or separation from daily-use identity | Productivity suite | 3 | 5 | 15 | High (15-25) | 5 | Enable MFA; separate admin identity from daily-use account. | Security Lead | Week 1 | Open
R-03 | Secrets | Credentials or API keys at risk of being committed to source control | Source control | 3 | 5 | 15 | High (15-25) | 5 | Enable secret scanning and push protection; rotate anything found; move all secrets to environment variables. | Security Lead | Week 1 | Open
R-04 | Availability | Backups taken but never restore-tested | Database service | 4 | 4 | 16 | High (15-25) | 6 | Perform and document one restore test per application; schedule quarterly. | Security Lead | Week 2 | Open
R-05 | Access | Single administrator across all systems with no documented recovery path | All systems | 3 | 5 | 15 | High (15-25) | 5 | Document a break-glass procedure; store recovery codes in a sealed offline location; name a trusted contact. | Security Lead | Week 2 | Open
R-06 | Third party | No data processing agreement with subprocessors handling personal data | Cloud services | 4 | 3 | 12 | Medium (8-14) | 5 | Accept each provider's DPA; keep copies; maintain a subprocessor list. | Security Lead | Week 3 | Open
R-07 | Privacy | Applications collecting personal data without a published privacy notice or deletion route | Hosted applications | 4 | 4 | 16 | High (15-25) | 6 | Publish a privacy notice per app; implement account deletion; document the lawful basis. | Security Lead | Week 3 | Open
R-08 | Vulnerability | Application dependencies not monitored for known vulnerabilities | Hosted applications | 4 | 4 | 16 | High (15-25) | 6 | Enable Dependabot alerts on every repository; set a remediation SLA by severity. | Security Lead | Week 2 | Open
R-09 | Asset | Unmaintained deployments potentially still reachable from the internet | Hosted applications | 3 | 5 | 15 | High (15-25) | 5 | Complete the application inventory; decommission or lock down anything unmaintained. | Security Lead | Week 1 | Open
R-10 | AI | Metered AI service keys without spend caps or usage alerting | AI service | 3 | 4 | 12 | Medium (8-14) | 5 | Set hard spend limits and usage alerts on every AI provider account. | Security Lead | Week 2 | Open
R-11 | AI | No documented position on provider retention or training use of submitted data | Hosted applications | 4 | 3 | 12 | Medium (8-14) | 5 | Confirm each provider's data-use terms; disable training on customer data where offered; state it in the privacy notice. | Security Lead | Week 3 | Open
R-12 | Logging | No application or administrative access logging | Hosted applications | 4 | 3 | 12 | Medium (8-14) | 5 | Enable platform logs; define a retention period; review monthly. | Security Lead | Week 3 | Open
R-13 | Endpoint | Workstation holding source code, secrets and business records | Workstation | 3 | 4 | 12 | Medium (8-14) | 5 | Verify FileVault is on; enable Find My; enable automatic OS updates; screen lock under 5 minutes. | Security Lead | Week 1 | Open
R-14 | Change | Deployments promoted to production without review or documented rollback | Hosting platform | 4 | 3 | 12 | Medium (8-14) | 5 | Use preview deployments; require a self-review checklist before promoting; document rollback. | Security Lead | Week 3 | Open
R-15 | Payment | Payment integration scope not formally assessed against PCI DSS SAQ-A | Payment processor | 3 | 4 | 12 | Medium (8-14) | 5 | Confirm the integration keeps card data entirely on Stripe; complete SAQ-A; keep it on file. | Security Lead | Week 4 | Open
R-16 | Incident | No documented incident response plan | All systems | 3 | 4 | 12 | Medium (8-14) | 5 | Write a one-page IR plan: detect, contain, assess, notify, learn. | Security Lead | Week 3 | Open
R-17 | Contractual | Contractual security flow-down requirements not assessed | Contracts | 3 | 4 | 12 | Medium (8-14) | 5 | Review executed contracts for security flow-downs; if CUI is handled, run an 800-171 self-assessment. | Security Lead | Week 4 | Open
R-18 | Access | No access offboarding process for contractors | Productivity suite | 3 | 3 | 9 | Medium (8-14) | 4 | Maintain an access list; remove on engagement end; review quarterly. | Security Lead | Week 3 | Open
R-19 | Availability | Critical service accounts tied to a single personal identity | Productivity suite | 2 | 5 | 10 | Medium (8-14) | 4 | Move critical accounts to a role address (admin@); ensure recovery methods are current. | Security Lead | Week 2 | Open
R-20 | Documentation | No documented security policy set | Management system | 5 | 2 | 10 | Medium (8-14) | 4 | Adopt a minimal policy set: acceptable use, access control, incident response, vendor management, data protection. | Security Lead | Week 2 | Open
R-21 | Governance | Assessment performed first-party; no independent review | Management system | 5 | 2 | 10 | Medium (8-14) | 4 | Declare the conflict in every report; seek external review before relying on it commercially. | Security Lead | Week 4 | Open
R-22 | Availability | Source code held in a single location with no independent copy | Source control | 2 | 4 | 8 | Medium (8-14) | 4 | Keep an offline clone of every active repository; refresh monthly. | Security Lead | Week 4 | Open

## Method
Risk Register — Northgate Services LLC (genericized)
Version | v1.0 — September 2026
Prepared by | Moussa Touré — first-party assessment
Scoring | Likelihood 1-5 x Impact 1-5. Treat above 15; plan with a date 8-14; accept and monitor at or below 7.
Risk identification method | A fixed six-question set applied to every service in scope: who can access it and how is that access protected; what happens if control is lost; what happens if contents leak; how would anyone know something went wrong; who else has access and under what contract; what breaks if it disappears tomorrow.
Residual score | An ESTIMATE derived from a documented reduction assumption per risk band. It is not a re-score after control testing. Stated as a limitation rather than presented as measurement.
Declared conflict | Performed by the organisation's own principal. First-party assessment; does not substitute for independent audit.
Publication note | Risk descriptions and asset names are genericized. A real register names unremediated weaknesses at a named company and is not publishable.